## Cover Page
<VEHICLE_DRIVER_ACCOUNT_BOOK>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Abhishek singh, Sankuratri Venkatrao, Bebimarayam Gove, Javed Shaikh, Alfia Haider
| Role | Programming Analyst Trainee
Signature
| Date | 2022-10-30
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Sprint -1
Sprint Backlog <VEHICLE_DRIVER_ACCOUNT_BOOK>
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 |  | 8
Task_1 | Create code for Authorization service |  | ABHISHEK | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Create code for Authorization testing |  | VENKATRAO | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Devlop code for Authorization testing |  | ALFIA | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop code for login page |  | BEBIMARAYAM | Completed | 0.5 | 1 | 2 | 3 | 1 | 0
User Story #2 |  | 1
Task_1 | Devlop code for Homepage |  | VENKATRAO | Completed | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Develop code for Driver service |  | JAVED | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for driver testing |  | ABHISHEK | Completed | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code for Available Drivers |  | ALFIA | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #3 |  | 5
Task_1 | Develop code for Edit driver |  | BEBIMARAYAM | Completed | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop code for Add Driver |  | ABHISHEK | Completed | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for Vehicle service |  | JAVED | Completed | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Vehicle testing |  | VENKATRAO | Completed | 2 | 0.5 | 0 | 0 | 0 | 0
User Story #4 |  | 8
Task_1 | Develop code for Available Vehicle |  | PAVITHRA | Completed | 9 | 4 | 2 | 2 | 1 | 1
Task_2 | Develop code to Add vehicle |  | MEGHANA | Completed | 6 | 6 | 3 | 3 | 3 | 1
Task_3 | Develop code for Edit vehicle |  | SOUMYAKANTA | Completed | 6 | 2 | 8 | 8 | 1 | 0
Task_4 | Develop code for Booking service |  | JAVED | Completed | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
User Story #5 |  | 3
Task_1 | Develop code for Booking service |  | JAVED | Completed | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 | Develop code for Booking Testing |  | ALFIA | Completed | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 | Code for Booking list |  | BEBIMARAYAM | Completed | 9 | 9 | 9 | 4 | 3 | 3
Task_4 | Code for Add Booking |  | ABHISHEK | Completed | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -2
Sprint Backlog <ATM_MANAGEMENT_SYSTEM>
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 |  | 8
Task_1 | User can Register with their login Details |  | ABHISHEK | Completed | 7 | 5 | 3 | 3 | 5 | 0
Task_2 | Registered User can select the Driver service |  | VENKATRAO | Completed | 3 | 2 | 4 | 5 | 0 | 1
Task_3 | User can select the Available Drivers |  | ALFIA | Completed | 5 | 1.5 | 3 | 6 | 4 | 2
Task_4 | User can add driver |  | BEBIMARAYAM | Completed | 7 | 3 | 2 | 7 | 1 | 1
User Story #2 |  | 1
Task_1 | User can select Available vehicle |  | JAVED | Completed | 4.5 | 3 | 2.5 | 3.5 | 2 | 3
Task_2 | User can add vehicle |  | ABHISHEK | Completed | 3 | 5 | 5 | 3 | 4 | 1
Task_3 | User can Add Booking |  | ALFIA | Completed | 4 | 4 | 5 | 2 | 5 | 3
Task_4 | User can Logout |  | BEBIMARAYAM | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 38.5 | 28.5 | 33.5 | 34.5 | 22 | 11

## Data (hidden)
In-Progress
Completed
N/A